MAGER SOFTWARE PLC

WEEKLY PROGRESS REPORT

- Work Completed This Week

- Data Migration - Infrastructure Phase (Phase 1)

One of the most critical steps in preparing the Enderas office computers for an operating system upgrade was making sure that all important files and data were safely backed up before any changes were made. This week, our team successfully completed the full data migration process across all accessible computers.

All important files from every accessible computer have been transferred to external storage. This includes documents, records, and any data the staff relies on for day-to-day operations. By completing this step, we have ensured that no information will be lost during the upcoming operating system upgrade.

With the data migration now complete, the computers are ready for the next step: upgrading all systems to Windows 11. This upgrade will be carried out during our next scheduled visit to the Enderas office.

- Computer Migration Status

The table below reflects the current status of all 14 computers assessed at the Enderas office:

| No. | Brand | CPU | RAM | Migration Status |
| --- | --- | --- | --- | --- |
| 1 | Lenovo | Core i3 | 4 GB | Migration Complete |
| 2 | HP | Core i3 | 4 GB | Migration Complete |
| 3 | HP | Core i3 | 4 GB | Migration Complete |
| 4 | HP | — | — | Pending Access |
| 5 | HP | — | — | Server – Excluded |
| 6 | HP | Core i3 | 4 GB | Migration Complete |
| 7 | HP | — | — | Pending Power Cable |
| 8 | HP | Core i3 | 4 GB | Migration Complete |
| 9 | HP | — | — | Pending Access |
| 10 | HP | — | — | Pending Power Cable |
| 11 | Lenovo | Core i3 | 4 GB | Migration Complete |
| 12 | HP | — | — | Pending Access |
| 13 | HP | — | — | Pending Access |
| 14 | HP | Core i3 | 4 GB | Migration Complete |

Note: Computers 4, 7, 9, 10, 12, and 13 remain inaccessible due to password restrictions, missing power cables, or hardware issues. These will be addressed at the time of the Windows 11 upgrade visit. Computer 5 is a server machine and has been intentionally excluded from this process.

- Website Development — Completed (Phase 1)

The new Enderass National PLC website has been fully designed and developed. All pages, layouts, and features are built and ready for review. The website is 100% complete on our end.

We are now waiting for the Enderass team to review the website and provide their feedback. Once the feedback is received and any requested adjustments are made, the website will be ready for deployment and will be live for the public to access.

The completed website includes the following:

- Full website layout and page structure

- Design consistent with the Enderass brand identity

- All standard pages (Home, About, Services, Contact, etc.)

- Mobile-friendly and responsive design across all screen sizes

- Ready for integration with the auction management system once deployed

Current Status: Website development is 100% complete. Awaiting client review and feedback before proceeding to deployment.

Next Step: Enderas team to review the website and share any feedback or change requests with the Mager Software team.

- Digital Auction Management System - Development Progress (Phase 2)

Development of the Enderass Digital Auction Management System has continued at a strong pace this week. The system which covers both the web application and the mobile application  is now approximately 70% complete.

The development team is on track to complete the full system within the coming week, though a short delay is possible depending on final testing and integration work. All core features are being actively built and tested.

The following modules are currently developed or in active development:

- User Management - registration, login, role-based access control, and KYC (identity verification)

- Auction Management - creating, scheduling, and managing auction listings

- Bidding System - real-time bid placement and tracking

- Admin Dashboard - full control panel for administrators to manage users, auctions, and reports

- Mobile Application - a mobile version of the system for Android and iOS devices, mirroring the web platform

- Pending Requirements from Enderass National PLC

In order for Mager Software PLC to complete deployment and launch all developed solutions, we require the following items from the Enderass team. These are not technical issues on our side  they are items that only Enderas can provide, and their availability will directly determine how quickly we can go live.

- Server Credentials & Domain Access

To deploy both the website and the Digital Auction Management System to the internet, we need secure access credentials and a domain name. Specifically, we require:

- A registered domain name (e.g., enderasauction.com or similar) that Enderas will use as their official web address

- Web hosting server credentials - the login information for the hosting environment where the system will be deployed

- SSL certificate (if available) - this is used to secure the website with "https" and is required for any platform that handles sensitive user data or payments

Without these, the completed website and auction system cannot be moved from our development environment to a live, public-facing platform.

Action Required: Enderas to provide domain name, hosting credentials, and any existing SSL certificates to the Mager Software team as soon as possible.

- Website Content (Text, Images & Files)

A website is only as useful as the content it presents to its visitors. While we have built the full structure and design of the Enderas website, the actual content — the words, images, and documents that represent Enderas to the public — must come from the Enderas organization itself.

We are requesting the following content materials from the Enderas team:

- Official company description and "About Us" text - who Enderas is, what they do, and their mission

- Services descriptions - a clear explanation of each service Enderas offers, written in their preferred tone and language

- High-resolution photos and images - company photos, office images, team photos, auction event photos, or any other relevant visuals

- Contact information - official phone numbers, email addresses, physical office address, and working hours

- Any certificates, awards, or documents Enderas wishes to display publicly

- Social media links (Facebook, LinkedIn, Telegram, etc.) if applicable

- Any additional pages or content sections Enderas would like to include

Until this content is received, the website will remain in its current state - fully built but with placeholder content. We cannot publish the site without real, approved information from Enderas.

Action Required: Enderas to prepare and share all website content materials (text, images, documents, and contact details) with the Mager Software team at the earliest opportunity.

- Phase Progress Summary

- Phase Progress Status

| Phase | Description | Target | Current | Status |
| --- | --- | --- | --- | --- |
| Phase 1 | Infrastructure Assessment & Website | 100% | 95% | Near Complete |
| Phase 2 | Digital Auction Management System | 100% | 70% | In Progress |

- Detailed Component Progress

| Component | Progress | Status / Notes |
| --- | --- | --- |
| Requirements & Planning | 100% | Complete |
| Infrastructure Assessment | 100% | Complete |
| File Migration (Data Backup) | 100% | Complete |
| OS Upgrade (Windows 11) | 0% | Scheduled – Next Visit |
| Website Design & Development | 100% | Complete – Awaiting Feedback |
| Website Deployment | 0% | Pending Credentials & Content |
| UI/UX Design (Auction System) | 90% | Near Complete |
| Database Design | 85% | In Progress |
| Core System Development | 70% | In Progress |
| Mobile Application | 70% | In Progress |
| Testing | 0% | Not Started |
| Deployment | 0% | Not Started |

Overall Project Completion: 62%

The project has made significant progress this week. The infrastructure data migration is complete, the website is fully developed and awaiting client review, and the auction management system is advancing steadily toward completion. The key dependencies at this stage are the receipt of server credentials and website content from Enderas, without which deployment cannot proceed.

4   Planned Activities for Next Week

The following activities are planned for the upcoming reporting period

Infrastructure

- Visit the Enderas office and perform the full Windows 11 upgrade on all accessible computers

- Resolve access issues for computers 4, 7, 9, 10, 12, and 13 (in coordination with Enderas staff)

- Verify that all systems are functioning correctly after the upgrade

Website

- Receive and review client feedback on the completed website

- Implement any requested adjustments or changes

- Proceed to deployment once credentials and content are received from Enderas

Auction Management System

- Complete remaining development modules: notification services, reporting & analytics

- Conduct integration testing between web and mobile applications

- Prepare for User Acceptance Testing (UAT) with the Enderas team

- Target full system completion by end of next week (subject to any final adjustments)

Prepared by: Mager Software PLC Development Team

Date: June 25, 2026